# Hertz Insurance Replacement Lead Conversion optimisation Project Context, Scope, Objectives

## Background

- Hertz derives ~20% of its total North America revenue (~$2B annually) from the Insurance Replacement segment

- The Insurance Replacement segment involves providing rental cars to customers whose vehicles are being repaired or replaced after an accident, with rentals covered by insurance companies

- Enterprise dominates the segment with ~70% market share vs. Hertz’s ~30% share

- Hertz currently converts 67-70% of insurance-referred leads, representing a significant gap to best-in-class performance (~80%)

- Lost conversions represent $20-30M in immediate revenue opportunity, with additional strategic upside in market share capture

- Root causes of lost conversions are currently understood anecdotally but not quantified or systematically addressed

## Success metrics

- Improved conversion rates from 67-70% to 80%+ within 12-18 months.

- At least an additional 800 conversions per month would payback Carrara’s fees (60,000 USD) for the 6 weeks.

## Output

- Jupyter notebook report outlining the results of our hypothesis testing through the data and stakeholder interviews.

- Diagnostics report with quantification of failure steps & estimated contribution to loss conversion (and therefore uplift potential)

- ROI prioritization framework that balances revenue impact, implementation complexity, and time-to-value for potential interventions

## This is likely achieved by:

### Data analysis

- Use converted leads, unconverted leads, location data, and other provided data.

- Compare attributes and nature of converted leads vs unconverted leads, key differences / patterns.

- Leverage statistical analysis to understand what influence conversion rates up or down significantly

### Stakeholder interviews for operational insights

- Use emerging insights from the data to dive deeper with Hertz stakeholders, getting more fidelity on what actually happens on the ground which causes the failure modes

- Focus on outbound calling desk and customer contact process.

- Identify specific breakdowns (timing, trust, follow-up, call quality) and resource allocation needs.

- Recommend quick-win interventions (3–6 months) and highlight longer-term “big rocks” to tackle in 2026.

### Financial modeling

- Estimate the revenue impact of addressing each conversion barrier.

- Develop ROI-driven prioritization for resource deployment.

## Approach

The general approach for this project will be as follows:

### Phase 1: Data Onboarding

Receive sample data from Hertz - 1,000 rows across multiple HLES tables (CRESER, CRA001, CSPLIT, TRANSLOG, Conversion) - Familiarize with data formats, field definitions, and table relationships - Build data loading and validation scripts that will work when full production data arrives - Document any data quality issues or gaps discovered in samples

### Phase 2: Descriptive Analysis

Establish baseline understanding of conversion patterns - Calculate overall conversion rate and validate against Hertz’s reported 67-70% - Segment conversion rates by key attributes: - Insurance partner (cdp_name) - Time-to-first-contact (contact_range) - Contact channel (Counter vs HRD vs MMR) - Geography / location - Day of week / time patterns - Identify which segments over/under-perform baseline

### Phase 3: Hypothesis Testing

Systematically test each conversion failure hypothesis

Work through hypotheses documented in @docs/hypotheses.md using the hypothesis tester agent.

### Phase 3A: Call Quality Analysis (New - HRD Call Center Data)

Analyze HRD call center operations and quality patterns

Context: HRD call recording data received (1,000 calls, Nov 1-7, 2025). Cannot directly join to HLES conversion data, but provides valuable operational insights.

Analysis objectives: - Agent performance benchmarking: Identify top/bottom performers, document best practices - Call quality patterns: Analyze completion rates, hold times, technical issues - Temporal optimization: Identify optimal calling hours, avoid low-performance periods - Operational issues: Multi-call attempts, transfer failures, telephony problems - Triangulation with HLES: Correlate aggregate call quality patterns with conversion trends for same time period

Deliverables: - Call quality analysis notebook (notebooks/04_call_quality_analysis.ipynb) - Agent performance rankings and training recommendations - Operational improvement recommendations (call attempt limits, hold time alerts, telephony fixes) - Stakeholder interview questions based on call data patterns

Limitations: - No direct conversion indicator in call data (disposition codes 100% null) - No join key to link individual calls to HLES conversion outcomes - Analysis relies on temporal triangulation and aggregate pattern correlation

### Phase 4: Insights Synthesis

Compile findings into actionable deliverables - Consolidate all hypothesis tests into a master Jupyter notebook - Rank failure modes by estimated conversion impact - Identify top 3-5 drivers of lost conversions with quantified uplift potential

### Phase 5: Stakeholder Interview Preparation

Use data insights to brief survey questionnaire - Translate quantitative findings into targeted questions for field teams - Focus on understanding the “why” behind the patterns observed in data - Prepare specific scenarios to validate with HRD, counter staff, and field leadership - Incorporate call quality insights: - Agent performance variance (4.6x difference between top/bottom performers) - Hour 13 performance drop (54% customer hang-ups) - shift change? lunch break? - Multi-call attempt policies (one customer received 63 calls) - Telephony technical issues (6.7% agent phone disconnects) - Team ROUPE vs ROSS effectiveness differences

### Phase 6: Stakeholder Interviews

Ground-truth findings with operational reality - Interview outbound calling desk (HRD) on contact process and barriers - Interview counter/location staff on walk-up vs. pre-booked conversion - Interview field leadership on resource constraints and competitive dynamics - Capture anecdotes that explain or contradict data findings

### Phase 7: Experiment Design

Craft interventions based on validated insights - Prioritize failure modes by: revenue impact × feasibility × speed-to-implement - Design A/B test frameworks for quick-win interventions (3-6 month horizon) - Outline “big rock” initiatives requiring longer investment (2026 roadmap) - Develop ROI projections for each proposed intervention